## GANTT Semanal
PROYECTO VISIÓN POR COMPUTADOR
| 0 | 2023-09-20 |  | 2 H | 2H | 2H | 3H | 2H | 3H | 3H | 3H | 3H | 3H | 3H | 1H | 5H | 5H
Inicio Proyecto | 2023-09-20 |  | 2023-09-20 | 2023-09-27 | 2023-10-04 | 2023-10-11 | 2023-10-18 | 2023-10-25 | 2023-11-01 | 2023-11-08 | 2023-11-15 | 2023-11-22 | 2023-11-29 | 2023-12-06 | 2023-12-13 | 2023-12-20 | 2023-12-27
TAREA | INICIO | FIN
TRABAJAO | 2023-09-19 | 2024-01-02
ENTREGA 1 | 2023-09-20 | 2023-10-03
Planificación | 2023-09-20 | 2023-09-24
Creación Plantilla | 2023-09-20 | 2023-09-26
Búsqueda Temática | 2023-09-20 | 2023-09-26
Redacción 1º Entrega | 2023-09-27 | 2023-10-03
ENTREGA 2 | 2023-10-04 | 2023-10-31
Busqueda tecnológica | 2023-10-04 | 2023-10-24
Redacción 2ª Entrega | 2023-10-18 | 2023-10-31
ENTREGA 3 | 2023-11-01 | 2023-12-05
Creación Página Web | 2023-11-01 | 2023-11-07
Diseño Web (I) | 2023-11-08 | 2023-12-05
Programación (I) | 2023-11-01 | 2023-12-05
ENTREGA 4 | 2023-12-06 | 2024-01-02
Validación | 2023-12-06 | 2023-12-26
Programación (II) | 2023-12-13 | 2023-12-26
Diseño Web (II) | 2023-12-06 | 2023-12-26
Redacción 4ª Entrega | 2023-12-20 | 2024-01-02
Tiempo Invertido: 16 Reuniones + 3*H Primera entrega+9H Segunda Entrega+15H Tercera Entrega+14H Cuarta Entrega=57 Horas

## Calendario
PROYECTO VISIÓN POR COMPUTADOR | [9 empty] | Trabajo individual: 57 h-
|  |  | 0 | 2023-09-20 | 2023-09-20 | [6 empty] | 2023-09-27 | [6 empty] | 2023-10-04 | [6 empty] | 2023-10-11 | [6 empty] | 2023-10-18 | [6 empty] | 2023-10-25 | [6 empty] | 2023-11-01 | [6 empty] | 2023-11-08 | [6 empty] | 2023-11-15 | [6 empty] | 2023-11-22 | [6 empty] | 2023-11-29 | [6 empty] | 2023-12-06 | [6 empty] | 2023-12-13 | [6 empty] | 2023-12-20 | [6 empty] | 2023-12-27
| INICIO DEL PROYECTO |  | 2023-09-20 | time axis 2023-09-20 to 2024-01-02
TAREA | RESPONSABLE | PROGRESO | INICIO | FIN | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M | M | J | V | S | D | L | M
TRABAJAO |  | 13.59% | 2023-09-19 | 2024-01-02
ENTREGA 1 |  | 54.37% | 2023-09-20 | 2023-10-03
SEMANA 1 |  | 88.75% | 2023-09-20 | 2023-09-26
Creación Plantilla | Gustavo | 75% | 2023-09-20 | 2023-09-26
Planificación | Jorge | 100% | 2023-09-20 | 2023-09-26
Búsqueda Información | Todos | 100% | 2023-09-20 | 2023-09-26
Justificaicon Rol | Todos | 80% | 2023-09-20 | 2023-09-26
SEMANA 2 |  | 20% | 2023-09-27 | 2023-10-03
Justificar Tema | Gustavo | 0%
Cronograma | Jorge | 100%
Impacto Social/Econ | Ivonne | 0%
ODS | Micaela | 0%
ENTREGA 2 |  | 0% | 2023-10-04 | 2023-10-31
SEMANA 3 |  | 0%
Tarea 3.1 | Persona X | 0%
Tarea 3.2 | Persona X | 0%
Tarea 3.3 | Persona X | 0%
Tarea 3.4 | Persona X | 0%
Tarea 3.5 | Persona X | 0%
SEMANA 4 |  | 0%
Tarea 4.1 | Persona X | 0%
Tarea 4.2 | Persona X | 0%
Tarea 4.3 | Persona X | 0%
Tarea 4.4 | Persona X | 0%
Tarea 4.5 | Persona X | 0%
SEMANA 5 |  | 0%
Tarea 5.1 | Persona X | 0%
Tarea 5.2 | Persona X | 0%
Tarea 5.3 | Persona X | 0%
Tarea 5.4 | Persona X | 0%
Tarea 5.5 | Persona X | 0%
SEMANA 6 |  | 0%
Tarea 6.1 | Persona X | 0%
Tarea 6.2 | Persona X | 0%
Tarea 6.3 | Persona X | 0%
Tarea 6.4 | Persona X | 0%
Tarea 6.5 | Persona X | 0%
ENTREGA 3 |  | 0% | 2023-11-01 | 2023-12-05
SEMANA 7 |  | 0%
Tarea 7.1 | Persona X | 0%
Tarea 7.2 | Persona X | 0%
Tarea 7.3 | Persona X | 0%
Tarea 7.4 | Persona X | 0%
Tarea 7.5 | Persona X | 0%
SEMANA 8 |  | 0%
Tarea 8.1 | Persona X | 0%
Tarea 8.2 | Persona X | 0%
Tarea 8.3 | Persona X | 0%
Tarea 8.4 | Persona X | 0%
Tarea 8.5 | Persona X | 0%
SEMANA 9 |  | 0%
Tarea 9.1 | Persona X | 0%
Tarea 9.2 | Persona X | 0%
Tarea 9.3 | Persona X | 0%
Tarea 9.4 | Persona X | 0%
Tarea 9.5 | Persona X | 0%
SEMANA 10 |  | 0%
Tarea 10.1 | Persona X | 0%
Tarea 10.2 | Persona X | 0%
Tarea 10.3 | Persona X | 0%
Tarea 10.4 | Persona X | 0%
Tarea 10.5 | Persona X | 0%
ENTREGA 4 |  | 0% | 2023-12-06 | 2024-01-02
SEMANA 8 |  | 0%

## Auditoría Horas
Department | Responsible | Hours W1 | Hours W2 | Hours W3 | Hours W4 | Hours W5 | Hours W6 | Hours W7 | Hours W8 | Hours W9 | Hours W10 | Hours W11 | Hours W12 | Hours W13 | Hours W14 | Hours W15 | Meetings | TOTAL
Management | Jorge Guijarro | 4 | 1 | 1 | 1.5 | 1.5 | 1 | 0 | 1 | 7 | 7.5 | 7.5 | 0.5 | 0.5 | 1 | 7 | 15 | 57 | 41
Technological | Ivonne Quishpe | 1.5 | 1 | 2 | 2.5 | 2 | 2 | 0 | 2.5 | 0.5 | 1 | 5 | 1.5 | 1.5 | 1.5 | 8.5 | 15 | 48 | 41
Documentation | Gustavo Maldonado | 2 | 1 | 1 | 1.5 | 1.5 | 3 | 0 | 2.5 | 0 | 3 | 5 | 0.5 | 1 | 1 | 6.5 | 15 | 44.5 | 41
Programming | Josep María Barberá | 2 | 3 | - | 1 | 0.5 | 4 | 0 | 1.5 | 2 | 2 | 7 | 0.5 | 2 | 8 | 8 | 15 | 56.5 | 41
Testing and Validation | Micaela Cabrera | 1 | 1 | 3 | 1.5 | 1 | 2 | 0 | 1.5 | 0.5 | 5.5 | 6.5 | 2 | 1 | 2.5 | 7 | 15 | 51 | 41
257
Department | Responsible | Hours W1: TOTAL HOURS
Management | Jorge Guijarro | Hours W1: 57
Technological | Ivonne Quishpe | Hours W1: 48
Documentation | Gustavo Maldonado | Hours W1: 44.5
Programming | Josep María Barberá | Hours W1: 56.5
Testing and Validation | Micaela Cabrera | Hours W1: 51
257

## EDT
TÍTULO DEL PROYECTO | Proyecto Visión por Computador | FECHA | 2023-09-20
Computer Vision Project
1. First Delivery
1.1 Planning
1.2 Topic Search
1.3 Delivery Writing
1.1.1 Create work schedule
1.1.2 WBS
1.1.3 Gantt Chart
1.3.1 Template Creation
1.3.2 Justify Team Role
1.3.3 ODS. Social and Environmental Impact
1.3.4 Planning
1.3.5 Final Review
2. Second Delivery
2.1 Technological Research
2.2 Delivery Writting
2.1.1 Distributed search
2.1.2 Technology Choice
2.3.1 Write Report
2.3.2 Final Review
3. Third Delivery
3.1 Webpage
3.2 Programming
3.1.1 Webpage creation
3.1.2 Prototipe of Webpage design
3.3.1 Data Visualization
3.3.2 Data Preprocessing
3.3.3 Define Algorithm Architecture
4. Fourth Delivery
4.1 Validation
4.2 Programming
4.3 Webpage
4.1.1
Debugging
4.1.2
Cross validation
4.1.3
Confusion matrix
4.1.4
Swot matrix
4.1.5
Generalization of the results
4.2.1 Algorithm Implementation
4.2.2 Performance Measurement
4.2.3 Real-time Image Processing
4.3.1 Webpage Final design
4.4 Delivery Writing
4.4.1 Conclusions
4.4.2 Final Review